|  |  |  |  | Project Kickoff |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | PROJECT KICKOFF PLAN |  |  |  |  |  |  |  |  |
|  | TALENT GROWTH INITIATIVE |  |  |  |  |  |  |  |  |
|  | The Talent Growth Initiative focuses on employee development to enhance skills and career opportunities.By offering targeted training, mentorship, and growth programs, the initiative aims to boost performance and satisfaction. The project also seeks to identify leadership potential and encourage long-term retention. This will help foster a thriving work environment and strengthen the company’s future. |  |  |  |  |  |  |  |  |
|  | PROJECT STAGE |  | TASK EXPLAINED | RESPONSIBLE | DEADLINE |  | STATUS |  |  |
|  | EMPLOYEE ASSESSMENT |  | Skill Inventory | Brandon Robertson |  | 25-Mar-25 |  |  |  |
|  |  |  | • Evaluate current employee skill sets. |  |  |  |  |  |  |
|  |  |  | Identify Gaps | Alicia Gordon |  | 30-Mar-25 |  |  |  |
|  |  |  | • Pinpoint areas needing improvement. |  |  |  |  |  |  |
|  | LEADERSHIP IDENTIFICATION |  | Talent Review | Michael Jordan |  | 31-Mar-25 |  |  |  |
|  |  |  | • Highlight employees with leadership potential. |  |  |  |  |  |  |
|  |  |  | Role Succession Planning | Donovan Johnson |  | 2-Apr-25 |  | 85% |  |
|  |  |  | Build a pipeline for future leadership roles. |  |  |  |  |  |  |
|  |  |  | Leadership Interviews | Tracey Weatherspoon |  | 5-Apr-25 |  | 75% |  |
|  |  |  | • Engage with candidates for leadership readiness. |  |  |  |  |  |  |
|  | PROGRAM DEVELOPMENT |  | Design Workshops | Michael Jordan |  | 20-Apr-25 |  | 25% |  |
|  |  |  | • Develop employee skill-building workshops. |  |  |  |  |  |  |
|  |  |  | Develop Mentorships | Donovan Johnson |  | 24-Apr-25 |  | ⏹ |  |
|  |  |  | • Pair employees with experienced mentors. |  |  |  |  |  |  |
|  |  |  | Create Learning Modules | Tracey Weatherspoon |  | 16-May-25 |  | ⏹ |  |
|  |  |  | • Craft interactive online training materials. |  |  |  |  |  |  |
|  | IMPLEMENTATION PHASE |  | Launch Workshops | Brandon Robertson |  | 10-Jun-25 |  | ⏹ |  |
|  |  |  | • Conduct training sessions company-wide. |  |  |  |  |  |  |
|  |  |  | Introduce Mentorships | Sylvia Gonzales |  | 15-Jun-25 |  | ⏹ |  |
|  |  |  | • Kick off mentorship program with participants. |  |  |  |  |  |  |
|  |  |  | Deploy Learning Modules | Garry Norton |  | 20-Jun-25 |  | ⏹ |  |
|  |  |  | • Make training modules accessible to staff. |  |  |  |  |  |  |
|  |  |  | Monitor Participation | Donovan Johnson |  | 30-Jun-25 |  | ⏹ |  |
|  |  |  | • Track employee engagement in programs. |  |  |  |  |  |  |
|  | FEEDBACK COLLECTION |  | Gather Responses | Sarah Smith |  | 4-Jul-25 |  | ⏹ |  |
|  |  |  | • Survey employees for program feedback. |  |  |  |  |  |  |
|  |  |  | Monitor Outcomes | Donovan Johnson |  | 25-Jul-25 |  | ⏹ |  |
|  |  |  | • Track employee performance improvements. |  |  |  |  |  |  |
|  | EVALUATION STAGE |  | Analyze Data | Donovan Johnson |  | 1-Sep-25 |  | ⏹ |  |
|  |  |  | • Assess metrics of success and weaknesses. |  |  |  |  |  |  |
|  | OVERALL PROJECT STATUS / Reported: April 4, 2025 by Martha Osborn |  |  |  |  |  |  |  |  |
|  | Quality Report: | Initial response is positive; high satisfaction. |  |  |  |  |  |  |  |
|  | Timeline Report: | On track, all deadlines are being met. |  |  |  |  |  |  |  |
|  | Budget Report: | Managed effectively, with surplus available. |  |  |  |  |  |  |  |